## Tabelle1
Identified | Probability of occurence | Damage | Mitigation strategy | Person in charge | Risk factor
Loss of project on the Server | 0.01 | 9 | Local backups |  | 0.09
Local loss of projecfiles | 0.5 | 0.2 | Use of serverbased GitHub | All | 0.1
Technical problems | 0.05 | 5 | None |  | 0.25
Poor project planning | 0.05 | 6 | Use Jira | Sebastian | 0.3
Unclear system requirements | 0.1 | 6 | Use very specific specifications | Sebastian | 0.6
Project involves the use of new technology | 0.1 | 6 | Sebastian knows the technology Vaadin, so we need to keep him alive | Philipp | 0.6
Project progress not monitored closely enough | 0.7 | 1 | We roughly know the project, sooooo… we just don't care | - | 0.7
Continually changing requirements | 0.2 | 5 | Try not to change anything :p | Roman | 1
Project involves the use of technology that has not been used prior project | 0.5 | 2 | As long as Sebastian is in, no problem, so… | Philipp | 1
Personal shortfalls | 0.3 | 4 | Don't drink'n'drive | Sebastian, Roman | 1.2
Untesteted functions | 0.6 | 4 | Automated tests | Roman, Philipp, Sebastian | 2.4
Artificial deadlines | 0.4 | 6 | Better planning | Sebastian, Philipp | 2.4
Unrealistic time estimates | 0.5 | 6 | Plan better | Philipp, Sebastian | 3
Failure to manage end-user expectations | 0.5 | 6 | Carefule UI design, asking coworkers about a possible design | Philipp | 3
Team members expelled from university | 0.5 | 8 | Support of team members in repetition tests | Philipp | 4