## Tabelle1
UC Name | Documentation | UI Design | Database | Warmup Phase | Coding | Testing | Total w/o warmup | Total | FP
Comment at pinboards | 1:00 | 0:00 | 0:30 | 0:00 | 0:20 | 0:10 | 2:00 | 2:00 | 20
Surveys | 0:10 | 0:10 | 0:30 | 0:00 | 1:00 | 0:30 | 2:20 | 2:20 | 22
See Pinboards | 1:00 | 0:10 | 0:30 | 0:00 | 1:00 | 0:30 | 3:10 | 3:10 | 25
Search for a Bar | 1:00 | 0:30 | 0:10 | 0:00 | 1:30 | 0:30 | 3:40 | 3:40 | 27
Get bar informations | 1:00 | 1:30 | 0:30 | 0:00 | 0:30 | 0:40 | 4:10 | 4:10 | 29
Rate a bar | 1:00 | 1:30 | 0:30 | 2:30 | 1:30 | 0:20 | 4:50 | 7:20 | 29
Login | 1:00 | 0:30 | 0:30 | 3:00 | 3:00 | 1:00 | 6:00 | 9:00 | 31
See Maps | 1:00 | 1:00 | 0:30 | 2:00 | 3:30 | 0:30 | 6:30 | 8:30 | 32
Change personal information | 1:00 | 0:30 | 0:30 | 0:00 | 3:00 | 0:40 | 5:40 | 5:40 | 44
Register | 1:00 | 1:30 | 0:30 | 2:00 | 4:30 | 1:30 | 9:00 | 11:00 | 52
Search bar | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 27,2
Number of User Input (Ei) | 0 | x |  |  | 0 | 0 | User only reads
Number of User Outputs (EO) | 1 | x |  |  | 1 | 0 | Google returns a json object to the server, the user gets both the result list and a visual representation on the map.
Number of User Inquiries (EQ) | 1 |  | x |  | 1 | 0 | User sends a search string to the server
Number of Files (ILF) | 4 | x |  |  | 0 | 1 | The view, presenter and database class and mySQL database. A whole bar is read from the database
Number of External Interfaces (EIF) | 1 | x |  |  | 0 | 1 | Google retuns a lot of information
Login | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 31,2
Number of User Input (Ei) | 0 | x |  |  | 0 | 0 | User only asks to login
Number of User Outputs (EO) | 0 | x |  |  | 0 | 0
Number of User Inquiries (EQ) | 2 | x |  |  | 0 | 2 | User sends username and password
Number of Files (ILF) | 6 | x |  |  | 0 | 0 | The window, the UI, the design, the implementation, the database class, the mySQL database
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0 | No communication to the outside
Register | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 52
Number of User Input (Ei) | 10 |  | x |  | 1 | 10 | There are 10 user inputs, all form one Database Record
Number of User Outputs (EO) | 0 | x |  |  | 0 | 0
Number of User Inquiries (EQ) | 0 | x |  |  | 0 | 0
Number of Files (ILF) | 4 |  | x |  | 1 | 10 | View, Presenter, Database class, mySQL Database
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0
Surveys | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 22,4
Number of User Input (Ei) | 1 |  | x |  | 1 | 0 | The amount depends on the survey in the database. That makes presenting the survey more comlex
Number of User Outputs (EO) | 0 | x |  |  | 0 | 0 | Only some thank you notification is shown
Number of User Inquiries (EQ) | 0 | x |  |  | 0 | 0
Number of Files (ILF) | 4 | x |  |  | 0 | 0 | View, Presenter, Database, MySQL Databse
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0
See pinboards | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 25,3
Number of User Input (Ei) | 0 | x |  |  | 0 | 0
Number of User Outputs (EO) | 0 | x |  |  | 2 | 0
Number of User Inquiries (EQ) | 1 |  | x |  | 0 | 0 | A bar id is sent to server, the bar datastructure is complex
Number of Files (ILF) | 4 |  | x |  | 2 | 0 | View, Presenter, Database, MySQL Database, Model, Bar
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0
Get bar informations | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 29,25
Number of User Input (Ei) | 0 | x |  |  | 0 | 0
Number of User Outputs (EO) | 1 | x |  |  | 0 | 0
Number of User Inquiries (EQ) | 1 |  | x |  | 2 | 0
Number of Files (ILF) | 6 | x |  |  | 0 | 0 | View, Presenter, Database, Model,
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0
Rate bar | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 29,25
Number of User Input (Ei) | 1 | x |  |  | 1 | 0 | Influences the whole rating
Number of User Outputs (EO) | 0 | x |  |  | 0 | 0
Number of User Inquiries (EQ) | 0 | x |  |  | 0 | 0
Number of Files (ILF) | 6 |  | x |  | 0 | 0 | View, Presenter, Database Class, MySQL Database, Rating Class, Bar Class, Avg, as we need to calculate some stuff
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0
Comment at pinboards | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 20,15
Number of User Input (Ei) | 1 | x |  |  | 0 | 1
Number of User Outputs (EO) | 0 | x |  |  | 0 | 0
Number of User Inquiries (EQ) | 0 | x |  |  | 0 | 0
Number of Files (ILF) | 4 | x |  |  | 0 | 0 | View, Presenter, Database Class, MySQL Databse
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0
Change personal information | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 44,2
Number of User Input (Ei) | 10 |  | x |  | 1 | 0
Number of User Outputs (EO) | 0 | x |  |  | 0 | 0
Number of User Inquiries (EQ) | 0 | x |  |  | 0 | 0
Number of Files (ILF) | 4 | x |  |  | 0 | 0 | View, Presenter, Database Class, MySQL Databse
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0
See Maps | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 32,4
Number of User Input (Ei) | 0 | x |  |  | 0 | 0
Number of User Outputs (EO) | 0 | x |  |  | 0 | 0
Number of User Inquiries (EQ) | 1 | x |  |  | 0 | 0
Number of Files (ILF) | 5 | x |  |  | 0 | 0 | View, Presenter, Database Class, MySQL Database, Google Maps Plugin
Number of External Interfaces (EIF) | 1 |  | x |  | 1 | 0 | Google Maps
Set Tags | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 22,1
Number of User Input (Ei) | 1 | x |  |  | 0 | 1 | A Tag will be saved
Number of User Outputs (EO) | 0 | x |  |  | 0 | 0
Number of User Inquiries (EQ) | 1 | x |  |  | 0 | 0
Number of Files (ILF) | 4 | x |  |  | 0 | 0 | View, Presenter, Database Class, MySQL Database
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0
Administrate Bars | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 31
Number of User Input (Ei) | 4 | x |  |  | 0 | 4 | A complete bar needs to be saved
Number of User Outputs (EO) | 0 | x |  |  | 0 | 0
Number of User Inquiries (EQ) | 0 | x |  |  | 0 | 0
Number of Files (ILF) | 5 | x |  |  | 0 | 0 | View, Presenter, Bar Class, Database Class, MySQL Server
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0
Name | Count | Simple | Average | Complex | RET | DET | Reason | Function points | 0
Number of User Input (Ei) | 0 | x |  |  | 0 | 0
Number of User Outputs (EO) | 0 | x |  |  | 0 | 0
Number of User Inquiries (EQ) | 0 | x |  |  | 0 | 0
Number of Files (ILF) | 0 | x |  |  | 0 | 0
Number of External Interfaces (EIF) | 0 | x |  |  | 0 | 0