## Tabelle1
Identified | Probability of occurence (ranges from 0 to 1) | Damage (ranges from 0 to 10) | Mitigation strategy | Person in charge | Risk factor
Project involves the use of new technology, such as Vaadin or headless testing | 0.5 | 6 | Read the docs, use google to find solutions, find alternatives and use old and know technology where possible | Philipp | 3
Unrealistic time estimates | 0.5 | 6 | Use function points as estimation | Philipp | 3
Failure to manage end-user expectations | 0.5 | 6 | Carefule UI design, asking coworkers about a possible design. Constant redesign, using declarative designs for easy html like changes | Philipp | 3
Artificial deadlines | 0.4 | 6 | Better planning | Philipp | 2.4
Untesteted functions | 0.6 | 4 | Automated tests, integration tests using headless testing | Roman, Philipp | 2.4
Team members expelled from university | 1 | 2 | The amount of work was reduced by deciding on rather simple use cases | Philipp | 2
Continually changing requirements | 0.2 | 5 | Try to keep changes low, in case of changes balance the new workload in the team | Roman | 1
Personal shortfalls, sickness | 0.5 | 2 | Sickness occured. Worked harder in other periods of time. | Roman | 1
Project progress not monitored closely enough | 0.7 | 1 | Each tem member knows what to do, monitoring is mainly optional | - | 0.7
Unclear system requirements | 0.1 | 6 | Use very specific specifications, use the RUP templates to make everything as clear as possible | Philiüü | 0.6
Poor project planning | 0.05 | 6 | Use Jira | Philipp | 0.3
Technical problems, like a maven break down or corruption of git repo | 0.05 | 5 | Work accurate and try to avoid these problemes. If they occur find a solution on google, use backups to restore a working point or redo the work if changes were small |  | 0.25
Local loss of projecfiles | 0.5 | 0.2 | Use of serverbased GitHub | All | 0.1
Loss of project on the Server | 0.01 | 9 | Local backups |  | 0.09