## Tabelle1
UC Name | Documentation | UI Design | Database | Warmup Phase | Coding | Testing | Total w/o warmup | Total | Estimate | FP | Explaniation
Comment at pinboards | 1:00 | 0:00 | 0:30 | 0:00 | 0:20 | 0:10 | 2:00 | 2:00 | 2:47 | 11.05
See Pinboards | 1:00 | 0:10 | 0:30 | 0:00 | 1:00 | 0:30 | 3:10 | 3:10 | 3:27 | 13.65
Login | 1:00 | 0:30 | 0:30 | 3:00 | 1:30 | 1:00 | 4:30 | 7:30 | 3:56 | 15.6
Rate a bar | 1:00 | 1:30 | 0:30 | 2:30 | 2:00 | 0:20 | 5:20 | 7:50 | 4:25 | 17.5 | CSS with Vaadin, complete recode
Search for a Bar | 1:00 | 0:30 | 0:10 | 0:00 | 1:30 | 0:30 | 3:40 | 3:40 | 3:27 | 13.65
Get bar informations | 1:00 | 1:30 | 0:30 | 0:00 | 0:30 | 0:40 | 4:10 | 4:10 | 4:35 | 18.2
Surveys | 0:50 | 1:00 | 0:30 | 0:00 | 2:00 | 0:30 | 4:50 | 4:50 | 4:46 | 18.9
See Maps | 1:00 | 1:00 | 0:30 | 2:00 | 2:30 | 0:30 | 5:30 | 7:30 | 5:05 | 20.15
Change personal information | 1:00 | 0:30 | 0:30 | 0:00 | 1:00 | 0:40 | 3:40 | 3:40 | 7:13 | 28.6 | Reuse the Register files and functions
Register | 1:00 | 1:30 | 0:30 | 2:00 | 2:00 | 1:30 | 6:30 | 8:30 | 7:13 | 28.6
See Maps | [6 empty] | 0:00 | 0:00 | 5:05 | 20.15
Set Tags | [6 empty] | 0:00 | 0:00 | 2:47 | 11.05
Administrate Bars | [6 empty] | 0:00 | 0:00 | 4:16 | 16.9
Search bar | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | User only reads | 13.65
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 0 | 1 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 1 | 3
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 1 | 14 | Presenter, Bar Model |  |  |  | Time spent (w/o outliers) | Function Points (w/o outliers) | Velocity
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Google retuns a lot of information |  |  |  | 39.6667 | 157.3 | 3.9655
Login | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | User only asks to login | 15.6
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 2 | 3 | User sends username and password
Number of Files (ILF) | 3 | 1 | 0 | 0 | 0 | 0 | 21 | The window, the UI, the User model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | No communication to the outside
Register | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 10 | 1 | 0 | 0 | 1 | 10 | 30 | There are 10 user inputs, all form one Database Record | 28.6
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 2 | 1 | 0 | 0 | 1 | 10 | 14 | Presenter, User Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Surveys | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 1 | 1 | 3 | The amount depends on the survey in the database. That makes presenting the survey more comlex | 18.9
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 0 | 3
Number of Files (ILF) | 3 | 1 | 0 | 0 | 0 | 0 | 21 | Presenter, Bar Model, Question Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
See pinboards | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 13.65
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 0 | 2 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 1 | 3
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 2 | 14 | Presenter, Bar
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Get bar informations | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 18.2
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 0 | 5 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 2 | 0 | 3
Number of Files (ILF) | 3 | 1 | 0 | 0 | 0 | 0 | 21 | View, Presenter, Database, Model,
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Rate bar | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 0 | 1 | 0 | 1 | 25 | 4 | 25 single, clickable stars | 17.5
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 3 | 1 | 0 | 0 | 1 | 11 | 21 | Presenter, Rating Class, Bar Class. Influences many fields in the database
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Comment at pinboards | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 1 | 3 |  | 11.05
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, Bar model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Change personal information | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 10 | 1 | 0 | 0 | 1 | 10 | 30 |  | 28.6
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, User Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
See Maps | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) |  | 1 | 0 | 0 | 0 | 0 | 0 |  | 20.15
Number of User Outputs (EO) |  | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 0 | 3 |  | 5.0813
Number of Files (ILF) | 3 | 1 | 0 | 0 | 0 | 0 | 21 | Presenter, Bar Model, Map Class
Number of External Interfaces (EIF) | 1 | 0 | 1 | 0 | 5 | 30 | 7 | Google Maps
Set Tags | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 1 | 3 | A Tag will be saved | 11.05
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2.7865
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, Bar Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Administrate Bars | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 4 | 1 | 0 | 0 | 0 | 4 | 12 | A complete bar needs to be saved | 16.9
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 4.2617
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presnter, Bar Class
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Name | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0